## Current Status 2020
FACTORY ARRIVAL
Sr.No | Division | Merchandiser | Month | PPC Demand No | PPC Demand date | Elapsed Lead Time | Remaining Lead Time | Purchase Order | PO Date | PO TAT | P.O Quantity | Shipper | Product Description | Quantity shipped | Unit Value | Total Amount | Bank | Payment Term | Mode of Shipment | Incoterm | Supplier Delivery time | Standard Lead Time | Supplier Delivery Date | PP Sample Readiness Date | Actual Shipment Ready Date | Delay against supplier Lead Time | Delay above supplier lead time from 1 to 10 days | Delay above supplier lead time from 10 to 20 days | On Board | ETA At port | B/L / AWB # | Date | POL | Destination port | Mode of Clearance | EOU LIMIT UTILIZED | FETA | 1st Revision | 2nd Revision | 3rd Revision | Delay | Forwarder | C/A | Doc to Agent | Remarks
[6 empty] | 2026-08-13 | [6 empty] | CORDURA |  |  |  |  | LC/ADV/O/A,DA,DP |  | CNF/FOB/EXW
1 | Garments | Zeeshan | january | 1 | 2026-01-01 | 224 | -139 | D21-3010-01 | 2026-01-02 | 1 | 4600 | ABC | CORDURA | 45000 |  | 65250 |  | LC | SEA | FOB | 35 | 85 | 2026-02-06 |  | 2026-02-22 | -16 | 16 |  | 2026-03-01 | 2026-03-19 | JKHI2104049 | 2026-03-01 | KOREA | KARACHI | EOU |  | 2026-03-27 | 2026-03-30 | 2026-04-05 | 2026-04-10 | NO of days | seagul | ZAWA | 2026-03-10 | Received on 8/8/26 | when goods received, will show as P.O complete in suppliers master sheet
2 | GLOVES | Zeeshan | february | 2 | 2026-02-01 | 193 | -108 | 006-06-21. | 2026-02-02 | 1 |  | FG | SOFT SHELL | 10000 |  | 20000 |  | LC 6422 | SEA | FOB | 35 | 85 | 2026-03-09 | 2021-04-21 | 2026-03-15 |  |  |  | 30-05-2021 | 2026-06-18 | JKHI2105039 | 30-05-2021 | CHINA | KARACHI | SEXP-1210 |  | 2026-04-27 |  |  |  | no of days | TAQ | ABC | docs received in Bank (24-06-2021 | UNDER PROCESS
3 | Garments | Haroon | march | 3 | 2026-03-01 | 165 | -80 | PWII/004/04/21 | 2026-03-02 | 1 |  |  | LINING | 9000 |  | 15000 |  | TT | SEA | FOB | 35 | 85 | 2026-04-06 | 2021-04-21 | 2026-04-06 |  |  |  | 30-05-2021 | 2026-06-18 | JKHI2105039 | 30-05-2021 | CHINA | KARACHI |  |  | 2026-05-25 |  |  |  |  | EXPEDITOR | ABC |  | UNDER PROCESS
4 | JACKETS | Haroon | april | 4 | 2026-04-01 | 134 | -49 | PWI/010/03/21 | 2026-04-02 | 1 |  |  | CORDURA | 6000 |  | 10500 |  | DA | AIR | FOB | 35 | 85 | 2026-05-07 | 2021-04-21 | 2021-05-25 |  |  |  | 30-05-2021 | 2026-06-18 | JKHI2105039 | 30-05-2021 | CHINA | KARACHI | SEXP-1210 |  | 2026-06-25 |  |  |  |  | TAQ | TAQ |  | UNDER PROCESS
5 | WORKWEAR | Numan | may | 5 | 2026-05-01 | 104 | -14 | 001/02/21 | 2026-05-02 | 1 |  | HJ | MESH FABRIC | 10000 |  | 3000 |  | OA | AIR | EXW | 40 | 90 | 2026-06-11 | 2021-04-26 | 2026-06-11 |  |  |  | 2021-06-09 | 2026-06-16 | GXPEW21057429 | 2021-06-09 | Jiangsu | LAHORE | SEXP-985 |  | 2026-07-30 |  |  |  |  | EXPEDITOR | EXPEDITORS | docs awaited | UNDER PROCESS
6 | Garments | Haroon | june | 6 | 2026-06-01 | 73 | 12 | PWII/003/04/21 | 2026-06-02 | 1 |  | KL | PU LEATHER | 10000 |  | 2000 |  | DP | SEA | CNF | 35 | 85 | 2026-07-07 | 2021-06-10 | 20-06-2021 |  |  |  | 2021-06-24 | 2026-06-30 | GXPEW21067408 | 2026-06-30 | CHINA | DHL | SEXP- 985 |  | 2026-08-25 |  |  |  |  | SEAGUL | SEAGUL |  | UNDER PROCESS
7 | [11 empty] | IU | [6 empty] | COURIER | CNF
8
SEAM SEALING & ZIPPER
OTHER ACCESSORIES
1 | Column B | Category (column b), all categories in total (% vs total number of categories), show each category percentage in grpah, fabric wise, accessories, machinery and parts, import detail, (no of transaction in a year, quarterly, half yearly, monthly)
| Column C | All departments in total, Report on merchandisers / Departments in round graph with number of orders placed department wise with value, in a year, in a month, quarterly, half yearly, with continuing years history
| Column D | Report on months, how many orders placed in a month, in a year, each products wise, department wise, with value, show in graph/diagram
| Column E | No of demands generated by PPC/merchandising/other departments, in a year, in a month, quarterly, half yearly
2 |  | Monthly, quarterly, half yearly import detail within fiscal year or past years with value in PKR, USD, Euro, RMB, YEN, POUND STERLING)
3 | Column I | Report on no of purchase orders made in a year, in a month, quarterly, and half yearly
4 |  | Item code wise import histroy, no of shipments repeated within a year or past years, with unit v alue
| Column L | No of suppliers, product/supplier wise, quantity wise, orders placed in a year (total orders), in a month, quarterly, half yearly
5 |  | Suppliers history (Dash Board), PP samples first approval, second approval, third approval, no of shipments delivery within lead time agreed with suppliers, price and delay variation
| Column N | Quantity placed in a year, in a month, item/product wise, show ia diagram
6 |  | FETA vs lead time, Dash B oard
7 | Column O | Payments made in a year, in month, quarterly, half yearly, in USD, Euro, JPY, Yuan, show in a diagram
| Column P | No of Banks business did in fiscal year, monthly, quarterly, half yearly, and each bank's share in USD, PKR, Euro, Yen, Pound,show in diagram
8 | Column Q | Report on no of payment terms used in import transactions with each term wise value / show in pivotal table
| Column R | Mode of shipments done in a year, by sea, by air, by courier, each category with value
| Column R+S | No of shipments in term of INCOTERMS, did ex-work by air, ex-work by sea, CNF by Air, CNF by sea, FOB by Air, and FOB by sea, each category with import value.
9 |  | No of Insurance companies, business did in fiscal year, country wise, monthly, half yearly
| Column Y,Z,AA | Delay against supplier lead time, vs orders placed / delay against lead time from 1 to 10 days, from 11 to 20 days
| Column AF | No of POL from where imports effected
| Column AO | List of forwarders, No of transactions done, months wise, and in a year, value of shipments, freight cost, LCL and FCL shipments with value, freight value , make/show in a pivot table
| Column AO | Forwarder Dash Board, no of shipments did, by air, by sea, 1st ETD, 2nd ETD, 3ETD, 1ST ETA, 2ND ETA, 3RD ETA,
| Column AF | No of ports at origin , port wise history by air, by sea,
| Column AG | No of ports at destination, port wise history by air, by sea,
| Column R | shipments clearance history, by air, by sea, by courier,
Lead time history, 1st FETA, 2ND FETA, 3rd FETA , Delay within 7 days, 7 to 14 days, 14 days and above
Clearance history, no of agents, EACH AGENT'S HISTORY, shipments did clear by air, by sea,
Clearing agent's dash board, clearance within 5 working days, above 5 working days
Trans porter history and dash baord, how many transporters are working, business done in a year with value, any losses,detail of LCL and FCL cargo
Landing cost sheet
Monthly import and export volume
all shipments status in transit, near to load, arrived, under clearance
port wise activity
Trend analysis of all import shipments, product category wise
Monthly dashboard, weekly dashborad
Formulas:
Supplier Delivery Date = +[Supplier Delivery time]+[PO Date]
FETA = +[Standard Lead Time]+[PPC Demand date]
Date = +[On Board]
Date = +[ETA At port]
Note on A2: Author: WHITE = Order Proceeded/Under Production Blue = Shipment under loading Purple = PP Sample Required Orange = Shipment in transit GREEN= Shipment Under Clearance
Note on Q2: Author: GREEN = Full Paid BLUE= Partial Paid RED= Un Paid
Note on B4: NEED A SEPARATE SHEET SHOWING NUMBER OF DEPARTMENTS, AND HOW MANY ORDERS PLACED BY EACH DEPARTMENT, WITH VALUE, WITH FROM TO OPTION, DATA WILL BE TRANSFERRED FROM SUPPLIERS MASTER SHEET
Note on C4: Moazzam: NEED FORMULA , AS HOW MANY ORDER PLACED BY MERCHANDISERES IN A YEAR
Note on D4: Moazzam: NEED FORMULA , AS HOW MANY ORDER PLACED IN EACH MONTH AND IN A YEAR
Note on E4: Moazzam: HOW MANY DEMANDS GENERATED BY PPC DEPARTMENT MONTH WISE AND IN A YEAR PPD DEMAND ENTERED IN SUPPLIERS MASTER SHEET WILL ALSO AUTO REFLECT HERE
Note on I4: Moazzam: HOW MANY PO GENERATED MONTH WISE AND IN A YEAR DATA WILL BE COLLECTED FROM SUPPLIER MASTER SHEET
Note on K4: Moazzam: CALCULATE DELAY IN MAKING PO AGAINST DEMAND ISSUANCE DATE,GRACE TIME IS 2 DAYS , AFTER THAT DELAY WILL BE CALCULATED
Note on L4: Moazzam: QUANTITY ENTERED IN P.O WILLAUTO ENTER IN SUPPLIER DATA ENTRY FORM, MASTER SHEET AND ITS
Note on M4: Moazzam: CALCULATE NO OF SHIPPERS, AND ORDERS PLACED IN A MONTH AND IN YEAR DATA WILL BE COLLECTED FROM SUPPLIERS MASTER SHEET
Note on N4: Moazzam: CALCULATE NO OF PRODUCTS WITH QUANTITY ORDERED IN A MONTH AND IN YEAR
Note on Q4: Moazzam: CALCULATE CURRENCY PAID AGAINST ORDERS MONTH WISE AND IN A YEAR
Note on R4: Moazzam: REPORT ON NO OF BANKS AND BUSIINESS DID WITH BANKS IN AYEAR, QUARTERLY, HALF YEARLY, MONTHLY
Note on S4: Moazzam: CALCULATE MODE OF PAYMENT AGAINST EACH CATEGORY WITH VALUE
Note on U4: Moazzam: NO OF SHIPMENTS DONE IN ONE YEAR, NO OF SHIPMENTS BY SEA, BY AIR, BY COURIER, NO OF SHIPMENTS DONE MONTH WISE,
Note on Y4: Moazzam: Need toa dd formula 1/4 date of supplier delivery time
Note on AB4: Moazzam: need to add formula to calculate delay time from 1 to 10 dys for supplier evaluation
Note on AC4: Moazzam: need to add formula to calculate delay time from 1 to 10 dys for supplier evaluation
Note on AP4: Moazzam: NEED TO ADD FORMULA IF THERE IS ANY DELAY ABOVE FETA THIS WILL SHOW TOTAL DELAY
Note on AQ4: Moazzam: LIST OF FORWARDERS, NO OF TRANSACTIONS DONE, MONTH WISE, AND IN A YEAR
Note on AR4: Moazzam: LIST OF FORWARDERS, NO OF TRANSACTIONS DONE, MONTH WISE, AND IN A YEAR
Note on AT4: Moazzam: NO OF SHIPMENTS UNDER PROCESS, NDER LOGISTICS, UNDER CLEARANCE,

## Current Closed Files 2020
[35 empty] | Delay AGAINST FETA | [7 empty] | Delay / Standard Lead Time |  |  | Q.C QUALITY / LEAD TIME REPORT | [10 empty] | Bank | [10 empty] | Insurance |  |  |  | Logistics | [5 empty] | Clearance
SR .No | Category | Merchandiser | Month | PPC Demand No | PPC Demand date | Elapsed Lead Time | Remaining Lead Time in hand | Purchase Order | PO Date | PO TAT | P.O Quantity | Shipper | Description of Goods | Quantity shipped | AMOUNT | Payment Term | Mode of Shipment/Price Term | Supplier Lead time | Standard Lead Time | Supplier Delivery Date | PP Sample Readiness Date | Actual Shipment Ready Date | Delay against supplier Lead Time | Delay above supplier lead time from 1 to 10 days | Delay above supplier lead time from 10 to 20 days | On Board | ETA at Port | B/L / AWB # | Date | POL | Destination port | Mode of Clearance | EOU LIMIT UTILIZED | FETA | 1st Revision | 2nd Revision | 3rd Revision | Delay | Forw | C/A | Doc to Agent | Remarks / Received at warehouse | Delay against standard lead time 1 to 10 days | Delay against standard lead time 10 to 20 days | Delay Cause | QC Report Received Date | Order Qty | Rejected Qty | Less Qty | Claim Date | Report Received in Days | Q.C Report standard Time / Days | Q.C Report received above from 10 to 20 days | Q.C Report received above from 20 to 30 days | Material financial loss @ Q.C | PO Closed From ERP | Bank Name | TT or LC Number | Date | R.O.E | Bank charges @ Advance payment | Bank charges @ LC opening | Bank charges @ LC/DP Docs retirement | Total | Documents payment against LC or DP/ TT payment | Documents from Bank | Open Account/Avance payment settlement with Bank | Insurance company | Bill No | Date | Amount | Forwarder | Bill No | Date | Weight/CBM | Amount | Bill to Finance | Clearing Agent | G.D No | Date | Shipment Clearance Date | Bill No | Date | Amount
| Garmetns |  | Jan | [8 empty] | Samtex | Different Fabric Samples | 187 yds | 916 | open account | By Air | [12 empty] | Korea |  | Selection mode | [9 empty] | Received 30-01-2021 |  |  | Selection | [6 empty] | 10 |  |  |  |  | select option |  |  |  | manual | manual | manual |  |  | Date | select option | select option | manual |  | manual | select option | manual | manual | manual | manual | Date
Note on A4: Author: WHITE = Order Proceeded/Under Production Blue = Shipment under loading Purple = PP Sample Required Orange = Shipment in transit GREEN= Shipment Under Clearance
Note on P4: Author: GREEN = Full Paid BLUE= Partial Paid RED= Un Paid
Note on I11: Kamal Bhatti: Qty Moved from N2- L1 after 30 Days
Note on P348: Kamal Bhatti: under value $5 only. Payment will be transferred along with next shipment.
Note on P349: Kamal Bhatti: Under Value $5. Payment has been transferred locally.
Note on P361: Kamal Bhatti: Total Value is $1892 & Balance amount i.e. $546 are paid by Diana on 9/9/20.
Note on A363: Kamal Bhatti: Order Cancelled
Note on AB364: Kamal Bhatti: Vessel Arrival delayes from 19/9/20 to 24/9/20
Note on AB373: Kamal Bhatti: Due to Port Congestion vessel delay ed
Note on I374: Kamal Bhatti: Qty increased on 8/9/20 by PPC
Note on I375: Kamal Bhatti: Rana sb on holiday on 1/10/20
Note on P375: Kamal Bhatti: Under Value. Payment $242+Mold charges $90 will be transferred to supplier along with next order.
Note on P383: Kamal Bhatti: RMB payment by Diana on dated 15/9/20
Note on I392: Kamal Bhatti: Rana sb on holiday on 1/10/20
Note on P392: Kamal Bhatti: Under Value. Payment $242+Mold charges $90 will be transferred to supplier along with next order.
Note on A394: Kamal Bhatti: Order Cancelled by PPC on 22/10/20
Note on A397: Kamal Bhatti: As Per Mr. Moazzam, order cancelled & shifted to Jennifer agasint SR # 5335
Note on AA398: Kamal Bhatti: Vessel skipped & onboard date delayed for one week
Note on I399: Kamal Bhatti: ION not updated till 25/9/20
Note on I400: Kamal Bhatti: Drawing not updated till 22/9/20
Note on A409: Kamal Bhatti: Order Cancelled by PPC on 6/11/20
Note on W414: Kamal Bhatti: Due to Supplier's issue (Machine is out of order), shipment ready date is delayed for 3 weeks
Note on AA417: Kamal Bhatti: Vessel Skipped due to space issue
Note on A419: Kamal Bhatti: Order closed by Mr. Hafiz Imran on 16/11/20
Note on AA421: Kamal Bhatti: Vessel skipped due to space issue
Note on I430: Kamal Bhatti: Rana sb on holiday on 1/10/20. As per Mr. Moazzam, PO will be made after price confirmaiton.
Note on M440: Kamal Bhatti: Order Placed on 26/10/20 & revised on 7/11/20
Note on I442: Kamal Bhatti: Waseem changed company from L1 to N2 on 3/10/20
Note on N447: Kamal Bhatti: Ishfaq added 1500 M OCC Navy Navy 2 ply soft shell from SR # 5273 from N2 to L1 on 16/10/20
Note on N450: Kamal Bhatti: Ishfaq moved 2 ply soft shell Navy/Navy to SR # 5265 on 16/10/20 from N2 to L1.
Note on N453: Kamal Bhatti: Waseem decreased the quantity on 25/9/20 Again received revised emand sheet on 15/10/20 with increased quantity i.e. 15000 M.
Note on N454: Kamal Bhatti: PPC requested to take 700 M by air on 4/11/20
Note on N455: Kamal Bhatti: Quantities revised by PPC on 23/10/20
Note on N456: Kamal Bhatti: Order Placed on 26/10/20 & revised on 7/11/20
Note on M467: Kamal Bhatti: Order Placed on 3/12/20 & company & quantity revsied on 4/12/20
Note on P470: Kamal Bhatti: $40 will be adjusted of old SR # 5254 as settled already from supplier
Note on N473: Kamal Bhatti: Quantities revised by PPC on 23/10/20
Note on P474: Kamal Bhatti: $94.50 will be deducted of short quantity agaisnt SR # 5122 in SR # 5315 as per settlement with supplier
Note on P475: Kamal Bhatti: Under Value. Will be paid along with SR # 5474-B
Note on N476: Kamal Bhatti: Waseem decreased the quantities on 25/9/20
Note on N483: Kamal Bhatti: Order placed on 17/10/20 & revised quantites on 27/10/20 by PPC
Note on P490: Kamal Bhatti: Under Value i.e. $30. actural value has been paid by Dian in RMB
Note on N492: Kamal Bhatti: Order Received on 12/11/20 & Revised on 13/11/20 & again revised on 7/12/20
Note on I496: Kamal Bhatti: Order sent on 17/10/20 & increased the quantites on 21/11/20
Note on I498: Kamal Bhatti: Order Received on 30/11/20 & company changed on 7/12/20
Note on P499: Kamal Bhatti: $234.90 of SR # 5474-A will be paid along with SR # 5474-B
Note on N507: Kamal Bhatti: Order Placed on 26/10/20 & revised on 7/11/20
Note on N509: Kamal Bhatti: Order Placed by PPC on 21/10/20 & revised on 6/11/20
Note on N510: Kamal Bhatti: Order placed on 19/9/20 & waseem revised quantities on 21/9/20
Note on N516: Kamal Bhatti: Quantities revised by PPC on 23/10/20
Note on N517: Kamal Bhatti: Quantities revised by Waseem on 12/10/20
Note on N520: Kamal Bhatti: Order Placed on 26/10/20 & revised on 7/11/20
Note on I525: Kamal Bhatti: Order Placed on 13/11/20 & company changed after 30 days & again company changed on after 40 days
Note on I526: Kamal Bhatti: Qty Moved from N2-L1 after 35 Days
Note on N526: Kamal Bhatti: due to space issue 2 ply soft shell black/black will be stuffed in container only 2633 M. Balance quantity will come under SR # 5393-B
Note on M528: Kamal Bhatti: Order Placed on 20/11/20 & revised quantities on 4/12/20
Note on N538: Kamal Bhatti: Order Placed on 26/10/20 & revised on 7/11/20
Note on N548: Kamal Bhatti: Order Received on 23/10 & Quantity revised on 27/10/20 by PPC & again revised quantity on 5/11/20
Note on N554: Kamal Bhatti: Order Received on 23/10 & Quantity revised on 27/10/20 by PPC
Note on K559: Kamal Bhatti: Qty moved from N2 to L1
Note on N562: Kamal Bhatti: Order Placed by PPC on 21/10/20 & revised on 6/11/20
Note on P565: Kamal Bhatti: $47 paid for courier. Supplier will use his own courier for sending parcel.